## Overview
Hermes Agent — deployment & execution workbook
One sheet per execution-layer phase (mirrors hermes-agent/README.md). Rows are the action sequence; each names its expected input, example value, input source and verification. Complete phases in order — a phase starts only after the previous one's verifications pass.
Locked decisions (2026-07-13, docs/SCOPING.md): trigger = workflow-action component ¦ brain = Anthropic API ¦ scraping = zero-auth t.me/s/ web preview first ¦ HubSpot = dedicated private app, sandbox 49610528 before prod 9201667.
How to use / legend
Yellow cells |  | The ONLY cells to edit on the phase sheets: column H 'Your value (fill in)' and column I 'Status'.
Your value |  | Record the actual value you used for that action's expected input (never paste secrets — write where the secret is stored, e.g. 'in /opt/hermes-stack/.env').
Status |  | Pick TODO / DONE / N/A from the dropdown. DONE only after the row's verification passed.
Example row |  | e.g. input 'BRIDGE_PUBLIC_BASE_URL' -> Your value: 'https://agent.icalps.ch' ¦ Status: DONE
Phase | Sheet | Execution layer | Actions | Done | Progress
0 | 0-Prerequisites | none yet — collect every input before touching the VPS (README Phase 0) | 9 | 0 | 0%
1 | 1-VPS-Provision | hermes-agent/provision/setup-vps.sh (idempotent; installs companion stack to /opt/hermes-stack) | 6 | 0 | 0%
2 | 2-Hermes-Install | Nous Research official installer + hermes CLI (interactive wizard; workspace ~/.hermes) | 9 | 0 | 0%
3 | 3-Stack-Config | /opt/hermes-stack/.env + /opt/hermes-stack/scraper/sources.yaml, then first service start | 10 | 0 | 0%
4 | 4-TLS-Caddy | provision/Caddyfile -> /etc/caddy/Caddyfile (public edge; bridge stays on loopback) | 6 | 0 | 0%
5 | 5-HubSpot-Interop | HubSpot private-app UI + hubspot/workflow-action/hermes-trigger-hsmeta.json + hs CLI | 11 | 0 | 0%
6 | 6-Agent-Seed | skills/revops/ -> ~/.hermes/skills/ + hermes cron/webhook CLI | 6 | 0 | 0%
7 | 7-Validation | signed/unsigned curl + systemctl + a live sandbox workflow enrollment (sign-off record) | 5 | 0 | 0%
8 | 8-Prod-Cutover | prod private app + .env swap + hs project upload against prod (only after Phase 7 is fully green) | 6 | 0 | 0%
9 | 9-Operations | systemd/journalctl + hermes CLI + .env rotations (recurring; no fixed sequence) | 8 | 0 | 0%
|  | TOTAL | 76 | 0 | 0%

## 0-Prerequisites
Phase 0 — Prerequisites (inputs inventory)
Execution layer: none yet — collect every input before touching the VPS (README Phase 0)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Order/confirm the VPS | Hosting provider console (guide baseline: Hostinger KVM2) | VPS spec + root SSH access | Ubuntu 24.04, 2 vCPU / 8 GB RAM, root key | Hosting provider | ssh root@<vps-ip> logs in; lsb_release -a shows Ubuntu 22.04/24.04 |  | TODO | Bare install, NO Docker — the harness needs direct filesystem + terminal access
2 | Choose the bridge subdomain | Your DNS registrar console | Fully-qualified domain name (FQDN) | agent.example.com | Your DNS zone (open scoping item Q6) | You can create/edit A records in that zone |  | TODO | The exact URL HubSpot will call; also used to rebuild signed URIs
3 | Create the Anthropic API key (decided brain) | console.anthropic.com > API keys | ANTHROPIC_API_KEY (sk-ant-...) | sk-ant-api03-... | Anthropic Console | Key displayed once and stored in your password manager |  | TODO | Decision 2026-07-13: Anthropic API powers the agent brain
4 | Create the Telegram gateway bot | Telegram: chat with @BotFather > /newbot | Bot name ending in 'Bot'; returns TELEGRAM_BOT_TOKEN | 123456789:AAF...xyz | @BotFather | Token message received from @BotFather |  | TODO | This is the OWNER GATEWAY bot — not the scraping identity
5 | Get your numeric Telegram user ID | Telegram: chat with @userinfobot | Numeric user id for TELEGRAM_ALLOWED_USERS | 123456789 | @userinfobot | Bot replies with your numeric id |  | TODO | Without the allowlist anyone could drive your agent — keep default-deny
6 | Confirm HubSpot super-admin on both portals | hubspot.com login | Super-admin membership on sandbox + prod | sandbox 49610528, prod 9201667 | HubSpot org admin | Both portals visible in the account switcher with admin rights |  | TODO | Decision 2026-07-13: sandbox-first validation
7 | Authenticate the HubSpot CLI on both portals | hs auth (once per account) | Personal access key per portal | personal access key from app.hubspot.com/personal-access-key | HubSpot > Settings > personal access key | hs accounts list shows 49610528 and 9201667 |  | TODO | Needed in Phase 5 for hs project validate/upload
8 | Decide the Telegram channel list to scrape | Open https://t.me/s/<username> for each candidate | Public channel usernames + topic tags | somechannel -> tags [revops] | Your own sources (open scoping item Q4) | Each https://t.me/s/<username> page renders posts |  | TODO | Zero-auth web-preview mode reads only channels with a public preview
9 | Make this repo reachable from the VPS | GitHub > repo > Code (HTTPS) or deploy key | Clone URL (+ deploy key if private) | https://github.com/Wkayaobama/HB-Workflow.git | GitHub | git ls-remote <url> succeeds from your machine |  | TODO

## 1-VPS-Provision
Phase 1 — Provision the VPS
Execution layer: hermes-agent/provision/setup-vps.sh (idempotent; installs companion stack to /opt/hermes-stack)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | SSH into the VPS as root | ssh root@<vps-ip> | VPS IP + root SSH key | 203.0.113.10 | Phase 0 step 1 | Shell prompt as root (id -u -> 0) |  | TODO
2 | Clone the repository | git clone <repo-url> && cd HB-Workflow | Repo clone URL | https://github.com/Wkayaobama/HB-Workflow.git | Phase 0 step 9 | HB-Workflow directory exists with hermes-agent/ inside |  | TODO
3 | Run the bootstrap script | bash hermes-agent/provision/setup-vps.sh | None (must run as root) | - | This repo | Steps [1/6]..[6/6] print; ends with 'Done. Next steps' block |  | TODO | Safe to re-run after any repo update
4 | Check the firewall | ufw status | None | - | - | Status: active; only OpenSSH(22), 80/tcp, 443/tcp allowed |  | TODO | Bridge port 8787 stays loopback-only, never opened
5 | Check the systemd units are installed + enabled | systemctl list-unit-files ¦ grep hermes | None | - | - | hermes-bridge.service, hermes-scraper.service, hermes-scraper.timer listed as enabled |  | TODO | Enabled but NOT started until .env is filled (Phase 3)
6 | Check the env file was created with tight permissions | stat -c '%a %n' /opt/hermes-stack/.env | None | - | - | Mode 600 on /opt/hermes-stack/.env |  | TODO | Copied from .env.example; existing .env is never overwritten

## 2-Hermes-Install
Phase 2 — Install the Hermes harness
Execution layer: Nous Research official installer + hermes CLI (interactive wizard; workspace ~/.hermes)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Run the official installer | curl -fsSL https://hermes-agent.nousresearch.com/install.sh ¦ bash | None | - | hermes-agent.nousresearch.com | Installer wizard starts |  | TODO | github.com/NousResearch/hermes-agent
2 | Choose the setup mode | Installer menu | Menu choice: 'Full Setup' | Full Setup | Ottho guide S4 | Wizard proceeds to provider selection |  | TODO | Quick Setup routes through the Nous Portal instead of your own keys — do not use
3 | Configure the brain (decided: Anthropic) | Installer prompt (writes ~/.hermes/.env) | Provider 'anthropic' + ANTHROPIC_API_KEY | sk-ant-api03-... | Phase 0 step 3 | grep ANTHROPIC_API_KEY ~/.hermes/.env shows the key |  | TODO | Decision 2026-07-13
4 | Pick the model | hermes model | Model choice from the provider list | latest Claude model offered | hermes CLI | ~/.hermes/config.yaml shows the chosen model |  | TODO
5 | Set up the Telegram gateway | hermes gateway setup | TELEGRAM_BOT_TOKEN | 123456789:AAF...xyz | Phase 0 step 4 | Wizard accepts the token |  | TODO | Guide S5
6 | Restrict who can talk to the agent | TELEGRAM_ALLOWED_USERS in ~/.hermes/.env | Comma-separated numeric Telegram ids | 123456789 | Phase 0 step 5 | Variable set; unknown users get no reply |  | TODO | Hermes default-denies — keep it that way
7 | Install the gateway as a boot service | sudo hermes gateway install --system | Confirmation | y | - | systemctl status hermes-gateway -> active (running) |  | TODO | Restart later with: hermes gateway restart
8 | Smoke-test the gateway | Telegram: message the bot /start, then any text | A chat message | coucou | Your Telegram | The bot answers |  | TODO
9 | Verify the workspace layout | ls ~/.hermes | None | - | - | config.yaml, .env, SOUL.md, memories/, skills/, cron/ present |  | TODO | /root/.hermes on a root install — matches stack .env defaults

## 3-Stack-Config
Phase 3 — Configure the companion stack
Execution layer: /opt/hermes-stack/.env + /opt/hermes-stack/scraper/sources.yaml, then first service start
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Set the harness workspace paths | vi /opt/hermes-stack/.env | HERMES_HOME / HERMES_INBOX_DIR / KNOWLEDGE_DIR | /root/.hermes ¦ /root/.hermes/inbox ¦ /root/.hermes/knowledge/revops | Phase 2 step 9 | Paths exist (mkdir -p the inbox/knowledge dirs) |  | TODO | Defaults fit a root install — only change for a non-root harness user
2 | Generate the bridge shared secret | openssl rand -hex 32 | HERMES_WEBHOOK_SECRET (64 hex chars) | 9f2c...64-hex...ab | Generated on the VPS | Value present in .env; SAME value reused on the HubSpot side later |  | TODO | Used by the custom-code fallback + signed curl smoke tests
3 | Set the public bridge URL | vi /opt/hermes-stack/.env | BRIDGE_PUBLIC_BASE_URL (https, no trailing slash) | https://agent.example.com | Phase 0 step 2 | Matches the Caddy domain EXACTLY |  | TODO | Used to rebuild the signed URI for HubSpot v2/v3 signature checks
4 | Leave HubSpot keys pending (filled in Phase 5) | vi /opt/hermes-stack/.env | HUBSPOT_PRIVATE_APP_TOKEN, HUBSPOT_CLIENT_SECRET | (empty for now); HUBSPOT_PORTAL_ID=49610528 | Phase 5 | HUBSPOT_PORTAL_ID already reads 49610528 (sandbox-first default) |  | TODO | Decision 2026-07-13: sandbox before prod
5 | Leave Telegram MTProto keys empty (decided: web-preview mode) | vi /opt/hermes-stack/.env | TELEGRAM_API_ID / TELEGRAM_API_HASH / TELEGRAM_SESSION | (all empty) | Decision 2026-07-13 | Scraper runs in zero-auth t.me/s/ mode (~20 posts/channel/run) |  | TODO | Filling all three later auto-switches to MTProto (see 9-Operations)
6 | Optional: instant-pickup accelerator | vi /opt/hermes-stack/.env | HERMES_HOOK_URL (+ HERMES_HOOK_TOKEN) or HERMES_CLI_TEMPLATE | http://127.0.0.1:8644/webhooks/hermes-stack | Phase 6 step 6 (Hermes native webhook) | Leave commented until Phase 6 enables the webhook |  | TODO | Inbox file-drop + inbox-sweep cron already guarantees pickup
7 | Fill in the real channel list | vi /opt/hermes-stack/scraper/sources.yaml | channels[].username + tags (replace REPLACE_ME_*) | username: somechannel / tags: [revops] | Phase 0 step 8 | Every username renders at https://t.me/s/<username> |  | TODO | mode: auto is correct; tune topics keyword buckets while here
8 | Start the bridge + scraper timer | systemctl start hermes-bridge hermes-scraper.timer | None | - | - | systemctl status shows both active |  | TODO
9 | Health-check the bridge locally | curl -s localhost:8787/healthz | None | - | - | {"ok": true, "service": "hermes-bridge"} |  | TODO | Bridge binds 127.0.0.1:8787 only
10 | Run one manual scrape | systemctl start hermes-scraper && journalctl -u hermes-scraper -n 50 | None | - | - | Log shows fetched/kept counts per channel, no tracebacks; items in KNOWLEDGE_DIR/inbox/ |  | TODO | Timer then runs it 4x/day

## 4-TLS-Caddy
Phase 4 — TLS exposure
Execution layer: provision/Caddyfile -> /etc/caddy/Caddyfile (public edge; bridge stays on loopback)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Point DNS at the VPS | Registrar console: A record | A record: <subdomain> -> <vps-ip> | agent.example.com -> 203.0.113.10 | Phase 0 step 2 | dig +short agent.example.com returns the VPS IP |  | TODO | Do this BEFORE reloading Caddy (Let's Encrypt HTTP challenge)
2 | Install Caddy | apt-get install -y caddy | None | - | Ubuntu/Caddy repos | caddy version prints |  | TODO
3 | Install the stack Caddyfile | cp /opt/hermes-stack/provision/Caddyfile /etc/caddy/Caddyfile | None | - | This repo | File in place |  | TODO
4 | Set the real domain in the Caddyfile | vi /etc/caddy/Caddyfile | Your FQDN replacing the placeholder | agent.example.com | Phase 0 step 2 | caddy validate --config /etc/caddy/Caddyfile passes |  | TODO | Only /hooks/hubspot and /healthz are proxied; everything else 404s at the edge
5 | Reload Caddy | systemctl reload caddy | None | - | - | journalctl -u caddy shows the certificate obtained |  | TODO
6 | Verify public health endpoint + cert | curl -s https://agent.example.com/healthz | None | - | - | {"ok": true, ...} over valid TLS; curl https://agent.example.com/other -> 404 |  | TODO | This URL is what goes into the workflow-action actionUrl

## 5-HubSpot-Interop
Phase 5 — HubSpot interoperability (sandbox 49610528)
Execution layer: HubSpot private-app UI + hubspot/workflow-action/hermes-trigger-hsmeta.json + hs CLI
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | 5a. Create the dedicated private app (sandbox) | Sandbox 49610528: Settings > Integrations > Private apps > Create app | App name | Hermes Agent | Decision 2026-07-13 (dedicated app, sandbox first) | App created |  | TODO | Separate from the live IcAlps app — clean blast radius
2 | 5a. Grant CRM scopes | Private app > Scopes tab | 6 scopes | crm.objects.{contacts,companies,deals}.read + .write | skills/revops/hubspot-crm/SKILL.md | All 6 scopes listed on the app |  | TODO | Notes/Tasks engagements ride on these object scopes
3 | 5a. Copy the token into the stack env | vi /opt/hermes-stack/.env then systemctl restart hermes-bridge | HUBSPOT_PRIVATE_APP_TOKEN (pat-...), HUBSPOT_PORTAL_ID | pat-eu1-... / 49610528 | Private app > Auth tab | Bridge restarts clean (journalctl -u hermes-bridge) |  | TODO
4 | 5a. Verify agent-side CRM access | python3 /opt/hermes-stack/skills/revops/hubspot-crm/hs_api.py get-deal <deal-id> | A sandbox deal id | 36808247883 | Any test deal in sandbox | Deal JSON returned (name, stage, amount) |  | TODO | Runs with the .env token; proves outbound interop
5 | 5b. Set the action URL in the manifest | vi hermes-agent/hubspot/workflow-action/hermes-trigger-hsmeta.json | actionUrl | https://agent.example.com/hooks/hubspot | Phase 4 step 6 | actionUrl field holds the real bridge URL |  | TODO | Commit the change — the manifest is source-controlled
6 | 5b. Stage the component into the projects app | mkdir -p ui-extension/src/app/workflow-actions && cp hermes-agent/hubspot/workflow-action/hermes-trigger-hsmeta.json ui-extension/src/app/workflow-actions/ | None | - | This repo | File present under src/app/workflow-actions/ |  | TODO | Directory name 'workflow-actions' is mandatory (2026.03 platform)
7 | 5b. Validate + upload to sandbox | hs project validate && hs project upload (account 49610528) | hs account selection | 49610528 | Phase 0 step 7 | Build + deploy succeed in the project UI |  | TODO | Validate/build success does not imply runtime success — keep going
8 | 5b. Reauthorize the app install | Project > Distribution tab | Click reinstall/reauthorize if prompted | - | HubSpot UI | App shows installed with the new workflow action |  | TODO
9 | 5b. Wire the v2 signing secret | App Auth page -> vi /opt/hermes-stack/.env (HUBSPOT_CLIENT_SECRET) -> systemctl restart hermes-bridge | HUBSPOT_CLIENT_SECRET | (from the app's Auth page after upload) | HubSpot app settings | Secret set; bridge restarted |  | TODO | OPEN ITEM: if the static-auth 2026.03 app surfaces no secret, use a capability-token URL path enforced in Caddy — never run unauthenticated
10 | 5b. Build the sandbox trigger workflow | Sandbox: Automation > Workflows > Create (e.g. deal-based) | Enrollment trigger | Deal stage becomes 'Identified' (pipeline 763145477 / stage 1113385378 on sandbox) | Open scoping item Q1.3 (first trigger events) | Workflow saved with the enrollment trigger |  | TODO | Sandbox pipeline ids differ from prod — see ui-extension ARCHITECTURE S5
11 | 5b. Add the Trigger Hermes Agent action | Workflow > + > Trigger Hermes Agent | hermes_action input field | deal_review (or contact_enrich / company_brief / revops_digest / custom) | bridge/app.py TASK_TEMPLATES | Action added with a valid hermes_action |  | TODO | hermes_prompt is REQUIRED when hermes_action = custom

## 6-Agent-Seed
Phase 6 — Seed the agent
Execution layer: skills/revops/ -> ~/.hermes/skills/ + hermes cron/webhook CLI
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Copy the seed skills into the harness | cp -r /opt/hermes-stack/skills/revops /root/.hermes/skills/ | None | - | This repo | /root/.hermes/skills/revops/ holds revops-radar, hubspot-crm, inbox-sweep, skill-authoring |  | TODO | Hermes layout: skills/<category>/<skill>/SKILL.md
2 | Share the stack env with the agent's tools | grep -E '^(HUBSPOT_¦HERMES_INBOX_DIR¦KNOWLEDGE_DIR)' /opt/hermes-stack/.env >> /root/.hermes/.env | None | - | Stack .env (Phases 3+5) | HubSpot token + paths appear in ~/.hermes/.env |  | TODO | Lets hs_api.py run from inside the agent
3 | Reload skills | Telegram: /reload-skills | None | - | - | Bot lists the four revops skills |  | TODO
4 | Run the self-configuration interview | Telegram: ask the agent to interview you to auto-configure | Your answers: who you are, RevOps focus, HubSpot context, tone | (free-form chat) | Guide S6 | SOUL.md / memories updated by the agent |  | TODO
5 | Create the inbox-sweep heartbeat | hermes cron create "5m" "Run the inbox-sweep skill" --name inbox-sweep | Interval + instruction + name | 5m / "Run the inbox-sweep skill" / inbox-sweep | skills/revops/inbox-sweep/SKILL.md | hermes cron list shows inbox-sweep |  | TODO | THIS turns the file inbox into a live queue — do not skip
6 | Optional: native webhook for instant pickup | ~/.hermes/.env: WEBHOOK_ENABLED=true, WEBHOOK_SECRET=...; hermes webhook subscribe; then set HERMES_HOOK_URL in /opt/hermes-stack/.env | WEBHOOK_SECRET + route | http://127.0.0.1:8644/webhooks/hermes-stack | hermes webhook --help | Bridge log shows hook delivery instead of inbox-only |  | TODO | Accelerator only; the 5m sweep already guarantees pickup

## 7-Validation
Phase 7 — End-to-end validation (all on sandbox)
Execution layer: signed/unsigned curl + systemctl + a live sandbox workflow enrollment (sign-off record)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Reject unsigned calls | curl -s -o /dev/null -w '%{http_code}' -X POST https://agent.example.com/hooks/hubspot -d '{}' | None | - | - | HTTP 401 |  | TODO | Proves the edge never accepts unauthenticated work
2 | Accept a signed call | Signed POST with X-Hermes-Timestamp + X-Hermes-Signature (HMAC-SHA256 of 'v0:<ts>:<body>' with HERMES_WEBHOOK_SECRET) | Body: action/objectType/objectId/portalId JSON | {"action":"deal_review","objectType":"deal","objectId":"123","portalId":"49610528"} | hermeslib/security.py header recipe | {"status":"queued","taskId":...} + task file in HERMES_INBOX_DIR |  | TODO | 5-minute replay window enforced
3 | Scrape-to-digest loop | systemctl start hermes-scraper | None | - | - | Items in KNOWLEDGE_DIR/inbox/; within ~5 min the agent sends a Telegram digest |  | TODO | Needs the inbox-sweep cron from Phase 6
4 | Workflow round-trip | Sandbox workflow: enroll one test deal | A test deal id | 36808247883 | Sandbox CRM | Bridge log 'via hubspot-v2'; Note written on the deal; action outputs hermes_status=queued + hermes_task_id |  | TODO | The core interop proof: HubSpot -> bridge -> agent -> HubSpot Note
5 | Reboot resilience | reboot, then re-check | None | - | - | hermes-gateway, hermes-bridge, hermes-scraper.timer, caddy all active; /healthz green |  | TODO | All units are enabled at boot by Phases 1-2

## 8-Prod-Cutover
Phase 8 — Prod cutover (9201667)
Execution layer: prod private app + .env swap + hs project upload against prod (only after Phase 7 is fully green)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Create the prod private app | Prod 9201667: Settings > Integrations > Private apps > Create 'Hermes Agent' | Same 6 CRM scopes as sandbox | crm.objects.{contacts,companies,deals}.read + .write | Phase 5a | App created on prod |  | TODO
2 | Swap the stack env to prod | vi /opt/hermes-stack/.env && systemctl restart hermes-bridge | HUBSPOT_PRIVATE_APP_TOKEN + HUBSPOT_PORTAL_ID | pat-eu1-...(prod) / 9201667 | Prod app Auth tab | Bridge restart clean; hs_api.py get-deal works against a prod deal |  | TODO
3 | Upload the workflow action to prod | hs project upload (account 9201667) + Distribution tab reauthorize | hs account selection | 9201667 | Phase 0 step 7 | Deploy succeeds; app reauthorized |  | TODO | Mind the LIVE IcAlps app: validate/build success != runtime success (ui-extension ARCHITECTURE S4)
4 | Update the signing secret if prod's differs | vi /opt/hermes-stack/.env (HUBSPOT_CLIENT_SECRET) && systemctl restart hermes-bridge | Prod HUBSPOT_CLIENT_SECRET | (from prod app Auth page) | HubSpot app settings | Bridge verifies prod-signed posts (log 'via hubspot-v2') |  | TODO
5 | Rebuild the trigger workflow on prod | Prod: Automation > Workflows (prod pipeline 766126206 / stage 1116419644 'Identified') | Enrollment trigger + hermes_action | deal_review on stage change | Phase 5b pattern | Workflow live, enrollment OFF or narrowed to one record |  | TODO | Prod pipeline ids differ from sandbox
6 | Single-record canary, then widen | Enroll ONE real record; verify; then widen enrollment criteria | One real deal id | (pick a low-stakes deal) | Prod CRM | Note appears on the record; no errors in bridge log; then widen |  | TODO | Keep the sandbox app + workflow as the permanent staging lane

## 9-Operations
Phase 9 — Steady-state operations
Execution layer: systemd/journalctl + hermes CLI + .env rotations (recurring; no fixed sequence)
Step | Action | Command / UI path | Expected input (name & format) | Example value | Input source | Verification / expected output | Your value (fill in) | Status | Notes
1 | Watch bridge logs live | journalctl -u hermes-bridge -f | None | - | - | Queued tasks + auth schemes visible per request |  | TODO
2 | Check the last scrape run | journalctl -u hermes-scraper -n 100 | None | - | - | fetched/kept counts, no tracebacks |  | TODO
3 | Check the scrape schedule | systemctl list-timers hermes-scraper.timer | None | - | - | Next run ~6h cadence (4x/day) |  | TODO
4 | Restart the agent gateway | hermes gateway restart | None | - | - | Bot answers on Telegram again |  | TODO
5 | Redeploy after a repo update | git pull && bash hermes-agent/provision/setup-vps.sh && systemctl restart hermes-bridge | None | - | This repo | Script re-runs idempotently; bridge healthy |  | TODO | .env and scraper state are preserved by the rsync excludes
6 | Rotate the webhook secret | openssl rand -hex 32 -> .env AND the HubSpot-side secret; systemctl restart hermes-bridge | New HERMES_WEBHOOK_SECRET (64 hex) | (fresh value) | Generated on the VPS | Old signature rejected (401), new accepted |  | TODO | Rotate both sides in one maintenance window
7 | Upgrade scraping to MTProto (when ready) | Locally: python3 hermes-agent/scraper/make_session.py; paste into VPS .env | TELEGRAM_API_ID + TELEGRAM_API_HASH + TELEGRAM_SESSION | api_id 1234567 / api_hash 32-hex / StringSession | my.telegram.org > API development tools (dedicated, aged, non-critical account) | Next scrape logs mtproto mode; full history + fetch_limit=30 honored |  | TODO | NEVER log in interactively on the VPS; datacenter-IP fresh logins are the flagging trigger
8 | Context hygiene | Telegram: prefer fresh conversations for new topics | None | - | Guide S8 | Quality stays high; durable memory lands in files |  | TODO | The seed skills already push file-based memory